## Sheet1
| Project name | Ninja Tutorial's website
| Test Designed By | Shubham SIrse
| Test Designed Date | 2025-04-02
| Peer revieve By | Shiv kumar
| Test Executed Date | 2025-09-02
Checkout
Test Scenario ID | Test Scenario | Test Case ID | Test Case | Test Case Description | Pre-requisite | Test Steps | Test Data | Expected Result | Actual Result | Status
TS-001 | Verify that users can proceed to checkout with items in the cart | TC-001 | verify the userCheckout with a single item | Ensure users can add one item to cart and proceed to checkout | User has an account, item available | 1. Log in tutorialsninja.com 2. Add one item 3. Click "Proceed to Checkout" | Selected item in cart | User should reach checkout page | Successfully redirected | Pass
|  | TC-002 | verify the user Checkout with multiple items | Ensure users can checkout with multiple items | User has an account, items available | 1. Log in tutorialsninja.com 2. Add multiple items 3. Click "Proceed to Checkout" | Multiple items in cart | Checkout should proceed with all items | Successfully proceeded | Pass
|  | TC-003 | verify the user Checkout with an empty cart | Ensure checkout is blocked when no items are in cart | No items in cart | 1. Click "Proceed to Checkout" | No items in cart | Checkout should be disabled | Checkout blocked | Pass
TS-002 | Validate guest checkout functionality without login | TC-005 | verify the user check Guest checkout availability | Ensure guest checkout option appears | User is not logged in | 1. Add item 2. Click "Proceed to Checkout" | Selected item in cart | Guest checkout option should appear | Guest checkout available | Pass
|  | TC-006 | verify the user Guest checkout with valid details | Ensure users can checkout with valid guest details | User is not logged in | 1. Add item 2. Proceed as guest 3. Enter valid details 4. Complete order | Valid shipping & billing details | Order should be placed | Order not placed | Fail
|  | TC-007 | verify the user Guest checkout with missing details | Ensure checkout is blocked if required fields are missing | User is not logged in | 1. Add item 2. Leave required fields blank 3. Try to checkout | Missing details | System should display an error | Error displayed | Pass
TS-003 | Ensure users can apply a discount/coupon code during checkout | TC-008 | verify the user Apply valid discount code | Ensure valid coupon codes are accepted | User has items in cart, valid coupon available | 1. Add item 2. Apply valid coupon 3. Proceed to checkout | Valid coupon | Discount should be applied | Discount not applied | Fail
|  | TC-009 | verify the user Apply expired coupon | Ensure expired coupon codes are rejected | User has items in cart, expired coupon available | 1. Add item 2. Apply expired coupon 3. Proceed to checkout | Expired coupon | System should show an error | Error displayed | Pass
|  | TC-010 | verify the user Apply invalid coupon format | Ensure invalid coupon format is rejected | User has items in cart | 1. Add item 2. Enter an invalid coupon format 3. Proceed to checkout | Invalid coupon | System should show an error | Error displayed | Pass
TS-004 | Check if users can select different payment methods | TC-010 | verify the user Select credit card payment | Ensure credit card payment is available | User has items in cart | 1. Proceed to checkout tutorialsninja.com 2. Choose credit card 3. Enter details 4. Complete payment | Valid credit card details | Payment should be processed | Payment successful | Pass
|  | TC-011 | verify the user Select UPI ( gpay, phonpay, paytm, amazonpay ,etc) payment | Ensure UPI ( gpay, phonpay, paytm, amazonpay ,etc) payment option is available | User has items in cart | 1. Proceed to checkout tutorialsninja.com 2. Choose UPI ( gpay, phonpay, paytm, amazonpay ,etc) 3. Complete payment | Valid UPI ( gpay, phonpay, paytm, amazonpay ,etc) account | Payment should be processed | Payment successful | Pass
|  | TC-012 | verify the user check and Select Cash on Delivery (COD) | Ensure COD option is available | User has items in cart | 1. Proceed to checkout tutorialsninja.com 2. Choose COD 3. Confirm order | COD option | Order should be placed without payment | Order placed | Pass
TS-005 | Verify that the system calculates total price correctly | TC-013 | verify the user check Price calculation with taxes | Ensure correct total price calculation with taxes | User has items in cart | 1. Proceed to checkout tutorialsninja.com 2. Verify total price includes tax | Items with tax | Total price should include tax | Price correct | Pass
|  | TC-014 | verify the user check Price calculation with shipping | Ensure correct total price calculation with shipping | User has items in cart | 1. Proceed to checkout tutorialsninja.com 2. Verify total price includes shipping | Items with shipping | Total price should include shipping | Shipping charge not included | Fail
|  | TC-015 | verify the user check Price calculation with discount | Ensure correct total price calculation after discount | User has items in cart, valid coupon | 1. Apply coupon 2. Verify discounted total | Discounted items | Total price should be reduced | Discount not applied price not reduced | Fail
TS-006 | Ensure shipping address fields accept valid inputs | TC-016 | verify the user check and Enter valid address | Ensure valid shipping addresses are accepted | User has items in cart | 1. Proceed to checkout 2. Enter valid address | Valid address | System should accept address | Address accepted | Pass
|  | TC-017 | verify the user check Enter incomplete address | Ensure incomplete addresses are rejected | User has items in cart | 1. Proceed to checkout tutorialsninja.com 2. Enter incomplete address | Incomplete address | System should show an error | Error displayed | Pass
|  | TC-018 | verify the user check Enter invalid address format | Ensure invalid addresses are rejected | User has items in cart | 1. Proceed to checkout tutorialsninja.com 2. Enter invalid address format | Invalid address | System should show an error | Error displayed | Pass
TS-007 | Check if users can modify/remove items before completing checkout | TC-019 | verify the user check Modify item quantity | Ensure users can update item quantity before checkout | User has items in cart | 1. Open cart 2. Change item quantity 3. Verify update | Updated quantity | Quantity should update | Quantity updated | Pass
|  | TC-020 | verify the user check Remove item from cart | Ensure users can remove items before checkout | User has items in cart | 1. Open cart 2. Remove an item 3. Verify update | Removed item | Item should disappear | Item removed | Pass
|  | TC-021 | verify the user check Clear entire cart | Ensure users can clear the cart before checkout | User has items in cart | 1. Click "Clear Cart" 2. Verify cart is empty | All items | Cart should be empty | Cart cleared | Pass
TS-008 | Verify that users receive order confirmation after successful payment | TC-022 | verify the user check Email confirmation | Ensure users receive an email confirmation | User completes checkout | 1. Complete order 2. Check email | Valid email | Email should be received | Email not received | Fail
|  | TC-023 | verify the user check Order confirmation page | Ensure users are redirected to the order confirmation page after checkout | User completes payment successfully | 1. Proceed to checkout tutorialsninja.com 2. Complete payment 3. Verify redirection | Valid order details | User should be redirected to the order confirmation page | Successfully redirected | Pass
|  | TC-024 | verify the user check Download invoice | Verify that users can download their invoice after completing the purchase | Order has been placed | 1. Navigate to the order confirmation page tutorialsninja.com 2. Click "Download Invoice" 3. Verify download | Completed order | Invoice should be downloaded | Invoice downloaded successfully | Pass
TS-009 | Test handling of failed payment scenarios | TC-025 | verify the user check Invalid card details | Ensure payment fails with invalid card details | User has items in cart | 1. Proceed to checkout tutorialsninja.com 2. Enter invalid card | Invalid card | Payment should fail | Payment failed | Pass
|  | TC-026 | verify the user check Insufficient balance | Ensure checkout is blocked if the user has insufficient funds | User has a card with insufficient balance | 1. Proceed to checkout tutorialsninja.com 2. Enter valid but insufficient balance card details 3. Click "Pay" | Low balance credit card | Payment should fail with an error message | Payment failed, error displayed | Pass
|  | TC-027 | verify the user check Payment gateway timeout | Verify system response when the payment gateway is unresponsive | Payment gateway experiences downtime | 1. Proceed to checkout tutorialsninja.com 2. Enter valid payment details 3. Click "Pay" | Valid payment details | System should show a timeout error | Timeout error not displayed | Fail
TS-010 | Verify that the checkout page is mobile-responsive | TC-028 | verify the user check Responsive layout | Ensure checkout page is responsive on different screens | User is on checkout page | 1. Open checkout on mobile tutorialsninja.com 2. Verify layout adapts | Mobile device | Page should adjust layout | Layout responsive | Pass
|  | TC-029 | verify the user check Touchscreen usability | Ensure all checkout elements are accessible on a touchscreen device | User accesses checkout on mobile | 1. Open checkout on mobile tutorialsninja.com 2. Try to click "Proceed to Checkout" and other buttons | Mobile device | All buttons should be clickable and functional | Buttons work as expected | Pass
|  | TC-030 | verify the user check Form field usability | Validate that input fields work properly on mobile | User enters checkout page on mobile | 1. Open checkout page tutorialsninja.com 2. Try entering details in the form fields | Mobile device | Fields should accept input properly | Input fields work correctly | Pass

## Sheet2
| Project name | Ninja Tutorial's website
| Test Designed By | Shubham SIrse
| Test Designed Date | 2025-04-02
| Peer revieve By | Shiv kumar
| Test Executed Date | 2025-09-02
|  |  | Special | Offer | Page
Test Scenario ID | Test Scenario | Test Case ID | Test Case | Test Case Description | Pre-requisite | Test Steps | Test Data | Expected Result | Actual Result | Status
TS-001 | Verify that all ongoing special offers are displayed correctly | TC-001 | verify that the user Display ongoing offers | Ensure that all ongoing special offers are visible | Special offers are active | 1. Navigate to the offers page tutorialsninja.com 2. Check if all active offers are displayed | List of active offers | All active offers should be displayed | Offers displayed correctly | Pass
|  | TC-002 | verify that the user offer details | Ensure each offer displays correct details (discount, validity, terms) | Special offers are active | 1. Open each offer tutorialsninja.com 2. Check if details match backend data | Offer details from backend | Details should be accurate | Details displayed correctly | Pass
|  | TC-003 | verify that the user Check visibility on homepage | Ensure major offers are highlighted on the homepage | Homepage should display offers | 1. Open homepage tutorialsninja.com 2. Check if major ongoing offers are displayed | Active homepage offers | Offers should be visible on the homepage | Offers not displayed on the homepage | Fail
TS-002 | Ensure expired deals are not visible to users | TC-004 | verify that the user check withHide expired offers | Ensure expired deals are not shown | Expired offers exist in the system | 1. Navigate to the offers page tutorialsninja.com 2. Verify expired offers are not displayed | Expired offers | Expired offers should not be visible | Expired offers hidden | Pass
|  | TC-005 | verify that the user Verify offer removal after expiration | Ensure offers disappear when they expire | Offer is active and near expiry | 1. Wait until offer expires 2. Refresh page 3. Verify offer is removed | Expired offer details | Expired offer should disappear | Offer removed successfully | Pass
|  | TC-006 | verify that the user Check expired offer in cart | Ensure expired offers do not apply at checkout | Offer added before expiry | 1. Add product to cart 2. Wait until offer expires 3. Proceed to checkout | Expired offer in cart | System should not allow expired discount | Offer removed from cart | Pass
TS-003 | Check that clicking on an offer redirects users to the correct product page | TC-007 | verify that the user Offer link redirection | Ensure clicking an offer redirects to the correct product page | Active special offers available | 1. Click on an offer 2. Verify if redirected to correct product page | Offer URL mapping | User should land on the correct product page | Redirected correctly | Pass
|  | TC-008 | verify that the user Check multiple offer links | Ensure all offers link correctly to their respective products | Multiple active offers | 1. Click on different offers 2. Verify each redirection | Offer-product mapping | All links should be correct | All links not working | Fail
|  | TC-009 | verify that the user Check broken offer links | Ensure there are no broken offer links | Active offers on the page | 1. Click on each offer link 2. Verify no "404 Page Not Found" error | Offer links | No broken links should exist | All links functional | Pass
TS-004 | Verify that promotional banners are displayed properly on different screen sizes | TC-010 | verify that the user Banner visibility on desktop | Ensure promotional banners are visible on desktop | Active banners available | 1. Open website on desktop tutorialsninja.com 2. Check if banner displays correctly | Desktop viewport | Banner should display properly | Banner displayed correctly | Pass
|  | TC-011 | verify that the user Banner visibility on mobile | Ensure promotional banners are responsive on mobile | Active banners available | 1. Open website on mobile tutorialsninja.com 2. Check banner display | Mobile viewport | Banner should adjust to screen size | Banner displayed correctly | Pass
|  | TC-012 | verify that the user Banner scaling on different resolutions | Ensure banners resize properly on different screen sizes | Active banners available | 1. Resize browser window tutorialsninja.com 2. Verify if banner adjusts correctly | Different screen resolutions | Banner should scale properly | Banner scaled not correctly | Fail
TS-005 | Ensure users can apply special offer codes at checkout | TC-013 | verify that the user Apply valid offer code | Ensure a valid offer code can be applied successfully | User has a valid offer code | 1. Add item to cart 2. Enter valid offer code 3. Apply discount | Valid offer code | Discount should be applied | Discount not applied | Fail
|  | TC-014 | verify that the user Apply expired offer code | Ensure an expired offer code is rejected | User enters an expired code | 1. Add item to cart 2. Enter expired offer code 3. Try to apply | Expired offer code | System should reject the code | Code rejected | Pass
|  | TC-015 | verify that the user Apply invalid offer code | Ensure an invalid offer code is rejected | User enters an incorrect code | 1. Add item to cart 2. Enter invalid code 3. Try to apply | Invalid offer code | System should reject the code | Code rejected | Pass
TS-006 | Validate that offers are applied correctly to eligible products | TC-016 | verify that the user Apply offer to eligible product | Ensure offer applies to the correct products | Active offers available | 1. Add an eligible product to cart 2. Apply offer | Eligible product | Discount should apply correctly | Discount not applied | Fail
|  | TC-017 | verify that the user Apply offer to non-eligible product | Ensure offer does not apply to ineligible products | Active offers available | 1. Add an ineligible product to cart 2. Apply offer | Non-eligible product | System should reject offer | Offer not applied | Pass
|  | TC-018 | verify that the user Check offer removal | Ensure discount is removed if product is removed from cart | Offer applied to product | 1. Add product to cart 2. Apply offer 3. Remove product | Product with discount | Discount should be removed | Discount removed | Pass
TS-007 | Ensure users get the correct discount in the cart when multiple offers are available | TC-019 | verify that the user Apply multiple offers | Ensure correct calculation when multiple offers are applied | Multiple active offers | 1. Add eligible products 2. Apply multiple offers 3. Check total price | Multiple offers | Correct discount should be applied | Discount not applied correctly | Fail
|  | TC-020 | verify that the user Verify offer stacking restrictions | Ensure that restricted offers do not stack | At least one offer should have stacking restrictions | 1. Add eligible product to cart 2. Apply two conflicting offers 3. Verify if system allows stacking | Offers with restrictions | System should prevent stacking of restricted offers | Stacking prevented successfully | Pass
|  | TC-021 | verify that the user Apply highest discount available | Ensure the highest discount is applied when multiple offers exist | Multiple offers available, but not stackable | 1. Add eligible product 2. Apply multiple offers 3. Verify that the highest discount is selected | Multiple offers with different discounts | System should automatically apply the best discount | Best discount not applied | Fail
TS-008 | Verify the functionality of countdown timers for limited-time deals | TC-022 | verify that the user Countdown timer visibility | Ensure countdown timer is visible for time-limited offers | Limited-time offer is active | 1. Navigate to the offer page tutorialsninja.com 2. Check if the countdown timer is displayed | Time-limited offer | Timer should be visible | Timer not displayed | Fail
|  | TC-023 | verify that the user Countdown timer expiration | Verify that the offer expires when the countdown reaches zero | Limited-time offer available | 1. Monitor countdown timer until it reaches zero 2. Refresh the page 3. Verify if the offer is removed | Expired limited-time offer | Offer should no longer be available | Offer removed after expiration | Pass
|  | TC-024 | verify that the user Timer accuracy check | Ensure countdown timer updates correctly in real-time | Active countdown timer | 1. Observe the countdown timer for 1 minute 2. Check if the timer updates accurately | Active timer | Timer should count down without delay or reset | Timer not updated correctly | Fail
TS-009 | Ensure offers cannot be applied after expiry | TC-025 | verify that the user Apply expired offer | Ensure expired offers are rejected | Expired offer exists | 1. Try to apply expired offer at checkout | Expired offer code | System should reject the offer | Offer rejected | Pass
|  | TC-026 | verify that the user Check expired offer visibility | Verify that expired offers are removed from the offers page | Expired offers are present in the system | 1. Navigate to offers page tutorialsninja.com 2. Search for expired offer | Expired offer | Expired offers should not be visible | Expired offers hidden | Pass
|  | TC-027 | verify that the user Validate cart removal of expired offer | Ensure that offers applied before expiry are removed at checkout | Offer applied before expiry | 1. Add product to cart with an active offer 2. Wait until offer expires 3. Proceed to checkout | Expired offer in cart | System should remove the expired offer | Offer removed from cart | Pass
TS-010 | Validate that offers update dynamically without page refresh | TC-028 | verify that the user Dynamic offer update | Ensure offers update without requiring page refresh | Dynamic pricing system enabled | 1. Apply offer 2. Wait for updated offer | Active dynamic offers | Offer updates automatically | Offer not updated correctly | Fail
|  | TC-029 | verify that the user Verify real-time discount update | Ensure that discount updates immediately when product quantity changes | Dynamic pricing system enabled | 1. Add product with an offer 2. Change quantity 3. Verify if discount updates instantly | Offer with dynamic pricing | Discount should adjust in real-time | Discount not updated correctly | Fail
|  | TC-030 | verify that the user Check offer auto-removal when ineligible | Ensure that ineligible products automatically lose applied offers | Dynamic pricing system enabled | 1. Add eligible product 2. Apply discount 3. Change product to an ineligible variant 4. Verify if discount is removed automatically | Ineligible product update | Discount should be removed automatically | Offer removed dynamically | Pass